## Project Plan
3B Michimap — SAP S/4HANA Brownfield Implementation Plan
Start Date: 21 Mar 2026 ¦ Total Duration: 24 weeks
Phase | Activity | Responsible | Discover |  | Prepare |  |  | Explore |  |  |  | Realize - Develop | [5 empty] | Realize - UAT |  |  | Deploy |  | Run
Week # |  |  | W1 21 Mar | W2 28 Mar | W3 04 Apr | W4 11 Apr | W5 18 Apr | W6 25 Apr | W7 02 May | W8 09 May | W9 16 May | W10 23 May | W11 30 May | W12 06 Jun | W13 13 Jun | W14 20 Jun | W15 27 Jun | W16 04 Jul | W17 11 Jul | W18 18 Jul | W19 25 Jul | W20 01 Aug | W21 08 Aug | W22 15 Aug | W23 22 Aug | W24 29 Aug
Discover | Run SAP Readiness Check 2.0 and review results (Simplification Items, Add-ons, Business Functions, Fiori Apps, Custom Code, Sizing) | Project Manager, Technical Consultant, Basis Administrator, Functional Consultant
Discover | Execute SAP Transformation Navigator assessment and define target architecture (S/4HANA edition, deployment, FES embedded vs hub) | Project Manager, Technical Consultant, Infrastructure Engineer, Customer Business Owner
Discover | Perform Custom Code analysis with ABAP Test Cockpit (ATC) incl. S/4HANA checks and baseline remediation approach | Technical Consultant, Functional Consultant
Discover | High-level process impact assessment using Simplification Item Catalog and business impact log | Functional Consultant, Customer Business Owner, Project Manager
Discover | Initial system landscape and downtime strategy assessment (DMO, ZDO options, SUM/DMO approach selection) | Basis Administrator, Technical Consultant, Infrastructure Engineer, Project Manager
Discover | Create project charter and initial project plan in SAP Cloud ALM (scope, milestones, governance, Q-Gates) | Project Manager, Customer Business Owner
Prepare | Set up SAP Cloud ALM for Implementation: project creation, team assignments, task plan import, governance setup | Project Manager, Technical Consultant
Prepare | Define system landscape and transport strategy (DEV/QAS/PRD, ChaRM/CTS, retrofit approach for conversion) | Project Manager, Basis Administrator, Technical Consultant
Prepare | Provision S/4HANA sandbox (copy/refresh from ECC) and prepare conversion toolchain prerequisites (SUM/DMO, SP levels) | Basis Administrator, Infrastructure Engineer, Technical Consultant
Prepare | Set up SAP Fiori infrastructure and initial launchpad concept (roles, catalogs, groups/spaces/pages) | Security Consultant, Basis Administrator, Technical Consultant
Prepare | Establish Test Management approach in SAP Cloud ALM (test strategy, test types, defect workflow, reporting) | Project Manager, Functional Consultant, Technical Consultant
Prepare | Define cutover strategy and high-level conversion runbook (mock conversions, dress rehearsal plan, freeze windows) | Project Manager, Basis Administrator, Functional Consultant
Prepare | Security and authorization concept baseline (SU24 review approach, SoD concept, emergency access, IAG plan if applicable) | Security Consultant, Project Manager, Customer Business Owner
Prepare | Interface inventory and integration approach confirmation (IDoc/RFC/PI/PO/CPI, connectivity, certificates) | Technical Consultant, Infrastructure Engineer, Functional Consultant
Explore | Perform System Conversion: run SUM/DMO in Sandbox incl. Pre-checks, SI checks, and baseline remediation log | Basis Administrator, Technical Consultant, Infrastructure Engineer
Explore | Execute Simplification Item checks (SI-Check) and resolve mandatory items for relevant LoBs (Finance, Logistics, HCM if in scope) | Functional Consultant, Technical Consultant, Basis Administrator
Explore | Finance conversion assessment: review prerequisites for New GL, Asset Accounting, Material Ledger, BP approach and CVI impacts | Functional Consultant, Technical Consultant, Customer Business Owner
Explore | CVI and Business Partner approach workshop and migration readiness (number ranges, roles, mapping, synchronization strategy) | Functional Consultant, Technical Consultant, Customer Business Owner
Explore | Fit-to-Standard workshop: Finance (Record-to-Report) focusing on S/4HANA differences and required configuration adjustments | Functional Consultant, Customer Business Owner, Project Manager
Explore | Fit-to-Standard workshop: Procurement (Source-to-Pay) including business partner, output management, and invoice processing changes | Functional Consultant, Customer Business Owner, Project Manager
Explore | Fit-to-Standard workshop: Sales (Order-to-Cash) including output management, pricing impacts, and credit management considerations | Functional Consultant, Customer Business Owner, Project Manager
Explore | Custom code remediation planning: classify findings (mandatory/optional), create backlog and assign owners (ATC results) | Technical Consultant, Functional Consultant, Project Manager
Explore | Integration impact analysis and interface adaptation backlog (IDoc segments, APIs, RFC, ALE, output management) | Technical Consultant, Functional Consultant, Infrastructure Engineer
Explore | Define testing scope and create initial end-to-end test cases in SAP Cloud ALM (E2E, regression, conversion validation) | Functional Consultant, Project Manager, Technical Consultant
Realize - Develop | Execute System Conversion: run SUM/DMO in Development system (DEV) and stabilize post-conversion technical layer | Basis Administrator, Technical Consultant, Infrastructure Engineer
Realize - Develop | Perform SPDD/SPAU and SPAU_ENH adjustments and transport results following retrofit/transport strategy | Technical Consultant, Basis Administrator
Realize - Develop | Implement mandatory Simplification Item remediation (e.g., credit management, output management, data model changes) | Functional Consultant, Technical Consultant
Realize - Develop | Custom code remediation execution (ATC findings) including performance optimization for HANA and CDS adaptations | Technical Consultant, Functional Consultant
Realize - Develop | Configure and run CVI/Business Partner synchronization in DEV and validate BP master data completeness | Functional Consultant, Technical Consultant, Security Consultant
Realize - Develop | Fiori enablement: activate relevant OData services, configure launchpad content (catalogs/spaces/pages) and roles | Security Consultant, Basis Administrator, Functional Consultant
Realize - Develop | Set up and validate Output Management (BRF+ / Adobe Forms) where applicable and adapt legacy outputs | Functional Consultant, Technical Consultant
Realize - Develop | Interface adaptations and connectivity setup (certificates, endpoints) and execute interface unit tests | Technical Consultant, Infrastructure Engineer, Functional Consultant
Realize - Develop | Set up Application Operations in SAP Cloud ALM (monitoring, alerting, job monitoring, integration monitoring) for converted systems | Technical Consultant, Basis Administrator, Project Manager
Realize - Develop | Prepare and execute SIT cycle in QAS (convert QAS, run E2E scenarios, defect triage in Cloud ALM) | Functional Consultant, Technical Consultant, Project Manager, Basis Administrator
Realize - UAT | Convert QAS/Pre-Prod (if separate) using SUM/DMO and perform post-conversion validation (technical smoke test) | Basis Administrator, Technical Consultant, Infrastructure Engineer
Realize - UAT | Execute UAT preparation: test plans, test packages, user provisioning, and UAT entry criteria sign-off in Cloud ALM | Project Manager, Functional Consultant, Security Consultant, Customer Business Owner
Realize - UAT | Run UAT Cycle 1 (end-to-end business process tests) and manage defects in SAP Cloud ALM (triage, prioritization, retest) | Customer Business Owner, Functional Consultant, Technical Consultant, Project Manager
Realize - UAT | Run UAT Cycle 2 / Regression testing focusing on critical processes and integration touchpoints | Customer Business Owner, Functional Consultant, Technical Consultant
Realize - UAT | Perform security role validation and SoD checks for UAT users (Fiori catalogs, critical authorizations, emergency access) | Security Consultant, Functional Consultant, Customer Business Owner
Realize - UAT | Execute performance and batch job validation (critical background jobs, spool, interfaces, MRP, settlement) in QAS | Basis Administrator, Technical Consultant, Functional Consultant
Realize - UAT | Finalize cutover plan and detailed runbook incl. downtime timeline, checkpoints, and rollback strategy | Project Manager, Basis Administrator, Functional Consultant, Technical Consultant
Realize - UAT | End-user training delivery for key changes (Fiori navigation, BP, output changes) and training material sign-off | Functional Consultant, Customer Business Owner, Project Manager
Deploy | Execute Production system conversion with SUM/DMO (including downtime execution and checkpoint reporting) | Basis Administrator, Technical Consultant, Infrastructure Engineer, Project Manager
Deploy | Perform post-go-live technical validation (system health checks, SLT/replication if any, jobs, interfaces, printing, monitoring setup) | Basis Administrator, Technical Consultant, Infrastructure Engineer
Deploy | Execute business validation (smoke tests) and go/no-go decision meeting | Customer Business Owner, Functional Consultant, Project Manager
Deploy | Production cutover execution: finalize transports, user/role provisioning, job scheduling, interface switch-over, communications | Project Manager, Basis Administrator, Security Consultant, Functional Consultant, Technical Consultant
Deploy | Hypercare setup in SAP Cloud ALM (issue categories, war room cadence, KPI dashboard, escalation paths) | Project Manager, Functional Consultant, Technical Consultant
Deploy | Confirm application operations monitoring and alert thresholds in SAP Cloud ALM for Production (jobs, interfaces, dumps, performance) | Technical Consultant, Basis Administrator, Project Manager
Run | Hypercare execution: manage incidents/defects in SAP Cloud ALM (triage, assignment, resolution, SLA tracking) | Project Manager, Functional Consultant, Technical Consultant, Basis Administrator
Run | Stabilization of business processes: daily operational checks and reconciliation for Finance and Logistics (period-end readiness) | Functional Consultant, Customer Business Owner
Run | Post-go-live security review: role fixes, SU24 adjustments, firefighter usage review, and audit evidence collection | Security Consultant, Functional Consultant
Run | Performance monitoring and tuning (SQL monitor/ST05 as needed, HANA memory/CPU trends, top dialogs) with corrective actions | Basis Administrator, Technical Consultant, Infrastructure Engineer
Run | Interface and batch job stabilization (failed IDocs, job runtimes, printing, output management issues) and preventive measures | Technical Consultant, Basis Administrator, Functional Consultant
Run | Operational handover to AMS/IT operations: finalize runbooks, monitoring ownership, and support procedures | Project Manager, Basis Administrator, Technical Consultant, Customer Business Owner
Run | Project closure in SAP Cloud ALM: lessons learned, final status report, and backlog transition to continuous improvement | Project Manager, Customer Business Owner, Functional Consultant, Technical Consultant

## Effort Estimation
3B Michimap — Effort Estimation ¦ Brownfield ¦ Start: 21 Mar 2026
Fill in effort (days) per phase per role. Rate, Total Days and Total Cost calculate automatically.
[5 empty] | Discover | Prepare | Explore | Realize - Develop | Realize - UAT | Deploy | Run
# | Role | Onsite / Offshore | Level | Rate (USD/day) | Discover (2w) | Prepare (3w) | Explore (4w) | Realize - Develop (6w) | Realize - UAT (3w) | Deploy (2w) | Run (4w) | Total Days | Total Cost (USD)
1 | Project Manager | Onsite | Senior | 1200 | [7 empty] | 0 | 0
2 | Programme Manager | Onsite | Principal Architect | 1500 | [7 empty] | 0 | 0
3 | Solution Architect | Onsite | Solution Architect | 1400 | [7 empty] | 0 | 0
4 | Functional Consultant – Finance | Offshore | Senior | 900 | [7 empty] | 0 | 0
5 | Functional Consultant – Finance | Offshore | Junior | 600 | [7 empty] | 0 | 0
6 | Functional Consultant – MM/SD | Offshore | Senior | 900 | [7 empty] | 0 | 0
7 | Functional Consultant – MM/SD | Offshore | Junior | 600 | [7 empty] | 0 | 0
8 | Functional Consultant – PP/QM | Offshore | Senior | 850 | [7 empty] | 0 | 0
9 | Technical Consultant – ABAP | Offshore | Senior | 800 | [7 empty] | 0 | 0
10 | Technical Consultant – ABAP | Offshore | Junior | 550 | [7 empty] | 0 | 0
11 | Technical Consultant – Integration | Offshore | Senior | 850 | [7 empty] | 0 | 0
12 | Basis Administrator | Offshore | Senior | 750 | [7 empty] | 0 | 0
13 | Security Consultant | Offshore | Senior | 750 | [7 empty] | 0 | 0
14 | Data Migration Specialist | Offshore | Senior | 800 | [7 empty] | 0 | 0
15 | Test Manager | Onsite | Senior | 1000 | [7 empty] | 0 | 0
16 | Change Management Lead | Onsite | Senior | 1100 | [7 empty] | 0 | 0
17 | Customer Business Owner | Onsite | Senior | 0 | [7 empty] | 0 | 0
18 | Infrastructure Engineer | Offshore | Senior | 700 | [7 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summary
3B Michimap — Effort Summary by Level ¦ Brownfield
Automatically summarised from Effort Estimation sheet. Fill in effort days there first.
| Discover | Prepare | Explore | Realize - Develop | Realize - UAT | Deploy | Run
Level | Discover | Prepare | Explore | Realize - Develop | Realize - UAT | Deploy | Run | Total Days | Total Cost (USD)
Junior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Principal Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onsite vs. Offshore Breakdown
Onsite | (see Effort Estimation sheet for per-phase detail) | [6 empty] | 0 | 0
Offshore | (see Effort Estimation sheet for per-phase detail) | [6 empty] | 0 | 0