## Project Plan
sss — SAP S/4HANA Pre-Sales Plan (Greenfield)
Phase Legend |  |  | Discover |  |  | Prepare |  |  |  | Explore | [5 empty] | Realize - Develop | [11 empty] | Realize - UAT | [5 empty] | Deploy |  | Run
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
Calendar Week |  |  | 22 Mar | 29 Mar | 5 Apr | 12 Apr | 19 Apr | 26 Apr | 3 May | 10 May | 17 May | 24 May | 31 May | 7 Jun | 14 Jun | 21 Jun | 28 Jun | 5 Jul | 12 Jul | 19 Jul | 26 Jul | 2 Aug | 9 Aug | 16 Aug | 23 Aug | 30 Aug | 6 Sep | 13 Sep | 20 Sep | 27 Sep | 4 Oct | 11 Oct | 18 Oct | 25 Oct | 1 Nov | 8 Nov | 15 Nov | 22 Nov | 29 Nov
Phase | Activity | Responsible | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37
Discover | Stakeholder Alignment & Vision Workshop | Project Team | bar: Discover 1 22 Mar W1 to Discover 3 5 Apr W3
| Current State Assessment | Project Team | bar: Discover 1 22 Mar W1 to Discover 3 5 Apr W3
| S/4HANA Business Case Development | Project Team | bar: Discover 1 22 Mar W1 to Discover 3 5 Apr W3
| Solution Scope Definition | Project Team | bar: Discover 1 22 Mar W1 to Discover 3 5 Apr W3
| High-Level Architecture Blueprint | Project Team | bar: Discover 1 22 Mar W1 to Discover 3 5 Apr W3
| Executive Sponsorship Alignment | Project Team | bar: Discover 1 22 Mar W1 to Discover 3 5 Apr W3
| Pre-Sales Presentation & Sign-Off | Project Team | bar: Discover 1 22 Mar W1 to Discover 3 5 Apr W3
Prepare | Project Charter & Governance Setup | Project Team | bar: Prepare 4 12 Apr W4 to Prepare 7 3 May W7
| SAP Activate Methodology Training | Project Team | bar: Prepare 4 12 Apr W4 to Prepare 7 3 May W7
| System Landscape Design | Project Team | bar: Prepare 4 12 Apr W4 to Prepare 7 3 May W7
| Project Standards & Templates | Project Team | bar: Prepare 4 12 Apr W4 to Prepare 7 3 May W7
| Risk Register Initialisation | Project Team | bar: Prepare 4 12 Apr W4 to Prepare 7 3 May W7
| Vendor & Partner Onboarding | Project Team | bar: Prepare 4 12 Apr W4 to Prepare 7 3 May W7
| Infrastructure Procurement Plan | Project Team | bar: Prepare 4 12 Apr W4 to Prepare 7 3 May W7
Explore | Fit-to-Standard Workshops (Finance) | Project Team | bar: Explore 8 10 May W8 to Explore 13 14 Jun W13
| Fit-to-Standard Workshops (SCM/Logistics) | Project Team | bar: Explore 8 10 May W8 to Explore 13 14 Jun W13
| Fit-to-Standard Workshops (HR/Payroll) | Project Team | bar: Explore 8 10 May W8 to Explore 13 14 Jun W13
| Delta Design Decisions Log | Project Team | bar: Explore 8 10 May W8 to Explore 13 14 Jun W13
| Integration Architecture Design | Project Team | bar: Explore 8 10 May W8 to Explore 13 14 Jun W13
| Data Migration Strategy | Project Team | bar: Explore 8 10 May W8 to Explore 13 14 Jun W13
| Master Data Governance Framework | Project Team | bar: Explore 8 10 May W8 to Explore 13 14 Jun W13
Realize - Develop | System Configuration – Core Finance | Project Team | bar: Realize - Develop 14 21 Jun W14 to Realize - Develop 25 6 Sep W25
| System Configuration – Procurement & Inventory | Project Team | bar: Realize - Develop 14 21 Jun W14 to Realize - Develop 25 6 Sep W25
| Custom Development (RICEFW) | Project Team | bar: Realize - Develop 14 21 Jun W14 to Realize - Develop 25 6 Sep W25
| Integration Development (CPI/BTP) | Project Team | bar: Realize - Develop 14 21 Jun W14 to Realize - Develop 25 6 Sep W25
| Unit Testing & Code Reviews | Project Team | bar: Realize - Develop 14 21 Jun W14 to Realize - Develop 25 6 Sep W25
| Master Data Load (Test Cycles) | Project Team | bar: Realize - Develop 14 21 Jun W14 to Realize - Develop 25 6 Sep W25
| Security & Authorisation Design | Project Team | bar: Realize - Develop 14 21 Jun W14 to Realize - Develop 25 6 Sep W25
Realize - UAT | User Acceptance Testing – Wave 1 | Project Team | bar: Realize - UAT 26 13 Sep W26 to Realize - UAT 31 18 Oct W31
| User Acceptance Testing – Wave 2 | Project Team | bar: Realize - UAT 26 13 Sep W26 to Realize - UAT 31 18 Oct W31
| Defect Management & Resolution | Project Team | bar: Realize - UAT 26 13 Sep W26 to Realize - UAT 31 18 Oct W31
| Cutover Strategy & Runbook | Project Team | bar: Realize - UAT 26 13 Sep W26 to Realize - UAT 31 18 Oct W31
| End-User Training Delivery | Project Team | bar: Realize - UAT 26 13 Sep W26 to Realize - UAT 31 18 Oct W31
| Performance & Volume Testing | Project Team | bar: Realize - UAT 26 13 Sep W26 to Realize - UAT 31 18 Oct W31
| Dress Rehearsal Go-Live Simulation | Project Team | bar: Realize - UAT 26 13 Sep W26 to Realize - UAT 31 18 Oct W31
Deploy | Production System Setup | Project Team | bar: Deploy 32 25 Oct W32 to Deploy 33 1 Nov W33
| Final Data Migration & Validation | Project Team | bar: Deploy 32 25 Oct W32 to Deploy 33 1 Nov W33
| Go-Live Cutover Execution | Project Team | bar: Deploy 32 25 Oct W32 to Deploy 33 1 Nov W33
| Hypercare Command Centre Setup | Project Team | bar: Deploy 32 25 Oct W32 to Deploy 33 1 Nov W33
| Post Go-Live Issue Resolution | Project Team | bar: Deploy 32 25 Oct W32 to Deploy 33 1 Nov W33
| Stabilisation Sign-Off | Project Team | bar: Deploy 32 25 Oct W32 to Deploy 33 1 Nov W33
| Handover to Support Team | Project Team | bar: Deploy 32 25 Oct W32 to Deploy 33 1 Nov W33
Run | Hypercare Support (Weeks 1–2) | Project Team | bar: Run 34 8 Nov W34 to Run 37 29 Nov W37
| Issue Triage & Resolution | Project Team | bar: Run 34 8 Nov W34 to Run 37 29 Nov W37
| Performance Monitoring & Tuning | Project Team | bar: Run 34 8 Nov W34 to Run 37 29 Nov W37
| Knowledge Transfer & Documentation | Project Team | bar: Run 34 8 Nov W34 to Run 37 29 Nov W37
| Project Closure & Lessons Learned | Project Team | bar: Run 34 8 Nov W34 to Run 37 29 Nov W37
| Centre of Excellence Establishment | Project Team | bar: Run 34 8 Nov W34 to Run 37 29 Nov W37
| Post-Implementation Review | Project Team | bar: Run 34 8 Nov W34 to Run 37 29 Nov W37
Resource Planning Matrix
Role | Description | Location | Level | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | Total
Solution Architect | Functional | Onsite | Discover 1 22 Mar W1: Sol. Architect |  | 0
SAP Functional Consultant | Functional | Onsite | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
SAP Functional Consultant | Functional | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
SAP Functional Consultant | Functional | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
SAP Technical Consultant | Technical | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
ABAP / BTP Developer | Technical | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
Integration Developer (CPI) | Technical | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
SAP Basis Administrator | Platform | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
Security Consultant | Technical | Onsite | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
Project Manager | Governance | Onsite | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
Service Delivery Manager | Governance | Onsite | Discover 1 22 Mar W1: SDM |  | 0
Change Management Lead | Governance | Onsite | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
QA / Test Lead | Quality | Onsite | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
Infra / Cloud Engineer | Platform | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
AI / Analytics Consultant | AI | Offshore | [38 empty] | 0 | bar: Discover 1 22 Mar W1 to Run 37 29 Nov W37
0
0
0
0
0
GRAND TOTAL (All Roles) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Resource Pivot
sss — Resource Effort Pivot by Year
Transition: Greenfield ¦ Total Weeks: 37 ¦ Model: gemini-1.5-flash
No | Role | Description | Location | Level | 2026 | Total
1 | Solution Architect | Functional | Onsite | Sol. Architect | 0 | 0
2 | SAP Functional Consultant | Functional | Onsite | Sr | 0 | 0
3 | SAP Functional Consultant | Functional | Offshore | Sr | 0 | 0
4 | SAP Functional Consultant | Functional | Offshore | Jr | 0 | 0
5 | SAP Technical Consultant | Technical | Offshore | Sr | 0 | 0
6 | ABAP / BTP Developer | Technical | Offshore | Jr | 0 | 0
7 | Integration Developer (CPI) | Technical | Offshore | Sr | 0 | 0
8 | SAP Basis Administrator | Platform | Offshore | Sr | 0 | 0
9 | Security Consultant | Technical | Onsite | Sr | 0 | 0
10 | Project Manager | Governance | Onsite | PM | 0 | 0
11 | Service Delivery Manager | Governance | Onsite | SDM | 0 | 0
12 | Change Management Lead | Governance | Onsite | Sr | 0 | 0
13 | QA / Test Lead | Quality | Onsite | Sr | 0 | 0
14 | Infra / Cloud Engineer | Platform | Offshore | Sr | 0 | 0
15 | AI / Analytics Consultant | AI | Offshore | Sr | 0 | 0
16 |  |  |  |  | 0 | 0
17 |  |  |  |  | 0 | 0
18 |  |  |  |  | 0 | 0
19 |  |  |  |  | 0 | 0
20 |  |  |  |  | 0 | 0
TOTAL |  |  |  |  | 0 | 0
Summary by Level
Level | Description | 2026 | Total
Jr | Junior | 0 | 0
Sr | Senior | 0 | 0
Sol. Architect | Solution Architect | 0 | 0
PM | Project Manager | 0 | 0
SDM | Service Delivery Manager | 0 | 0
Summary by Description
Category | 2026 | Total
Functional | 0 | 0
Technical | 0 | 0
Governance | 0 | 0
Quality | 0 | 0
Platform | 0 | 0
AI | 0 | 0